## Sheet1
Task Breakdown - Dynamic Excel Report Builder
1. Project Setup & Infrastructure
Set up development environment (React + Spring Boot + PostgreSQL)
Configure CI/CD pipeline (Docker, Kubernetes, GitHub Actions)
Set up cloud infrastructure (AWS S3, Redis)
Configure monitoring tools (Spring Actuator, Prometheus, Grafana)
2. Database Design & Implementation
Design and create database schema (users, roles, permissions tables)
Create materialized views (mv_user_access, domain-specific MVs)
Set up audit logging table
Configure database security (SSL/TLS, connection pooling)
Create indexes and optimize queries
3. Authentication & Authorization (RBAC)
Implement Spring Security with OAuth 2.0/JWT
Build role-based access control system
Implement department and hierarchy-based permissions
Create SQL access levels (Normal vs Technical users)
Integrate with materialized views for permission checks
4. LLM Integration
Select and configure LLM (fine-tuned model or external API)
Fine-tune LLM on domain-specific data (1,000-5,000 queries)
Build REST API wrapper for LLM
Implement query classification and relevance checking
Develop SQL generation logic
Create report type suggestion engine
5. Backend Development (Spring Boot)
Build REST API endpoints
Implement database connectivity layer
Create Excel generation service (Apache POI)
Build template management service
Implement SQL validation and sanitization
Create report versioning and storage system
Build audit logging service
6. Frontend Development (React)
Build chat interface UI
Create report type selection and preview components
Implement SQL editor panel (Monaco Editor for technical users)
Build template management UI (upload/edit/delete)
Create report download interface
Implement role-based UI rendering
Add responsive design and accessibility (WCAG 2.1)
7. Excel Report Generation
Implement Option 1 (custom template + data sheet)
Implement Option 2 (standard single-sheet report)
Build template validation logic
Create formula and chart generation
Implement conditional formatting
Add metadata (headers, footers, timestamps)
8. Template Management System
Build template upload functionality
Implement template storage (AWS S3)
Create template versioning system
Build template validation engine
Implement template CRUD operations
9. Testing
Unit testing (JUnit, React Testing Library)
Integration testing (API, database, LLM)
Security testing (SQL injection, authentication)
Performance testing (load testing for 500 concurrent users)
AI accuracy testing
SQL access control testing
End-to-end testing
10. Security Implementation
Implement encryption (SSL/TLS for all connections)
Add input sanitization and validation
Secure file download mechanism
Implement SQL injection prevention
Add audit trail for all operations
11. Performance Optimization
Implement caching (Redis, Spring Cache)
Optimize database queries and indexing
Configure async processing for report generation
Load balancer configuration
LLM response optimization
12. Documentation
API documentation
Database schema documentation
User manual (Normal and Technical users)
Developer documentation
Deployment guide
13. Deployment & Training
Deploy to cloud environment
Configure production monitoring
Conduct user training sessions
Prepare support materials
Go-live and handover